## Project 1 Tasks
Level | Task Name | Start | End | Duration | Status | Owner | Depends On | Notes
0 | Microblock 2.5 | 2026-04-17 | 2026-09-04 | 101 | In Progress
1 | Engineering design - pending tasks | 2026-04-17 | 2026-05-06 | 14 | In Progress
2 | Costing Estimate | 2026-04-24 | 2026-04-28 | 3 | Not Started
2 | Evap tray angle > 1 deg | 2026-04-17 | 2026-04-24 | 6 | Completed
2 | Rerouting evap fan wires | 2026-04-17 | 2026-04-24 | 6 | Completed
2 | Electrical harness | 2026-04-17 | 2026-04-24 | 6 | Completed
2 | DVP&R | 2026-04-17 | 2026-05-06 | 14 | In Progress
1 | Buy/Make parts - Initial prototypes | 2026-04-17 | 2026-07-02 | 55 | In Progress
2 | Case orders | 2026-04-17 | 2026-07-02 | 55 | In Progress
3 | PO | 2026-04-17 | 2026-04-23 | 5 | Completed
3 | Delivery | 2026-04-24 | 2026-07-02 | 50 | Not Started |  | PO
2 | Cassette base | 2026-04-17 | 2026-05-07 | 15 | In Progress
3 | CNC Routed | 2026-04-20 | 2026-04-28 | 7 | In Progress
3 | Foamed Base | 2026-04-17 | 2026-05-07 | 15 | In Progress
2 | Enclosure - CNC routed | 2026-04-17 | 2026-05-07 | 15 | In Progress
2 | Inidividual part orders | 2026-05-08 | 2026-05-12 | 3 | Not Started
2 | S/M Drawings for MS | 2026-05-13 | 2026-05-18 | 4 | Not Started
1 | Building prototypes | 2026-04-29 | 2026-05-05 | 5 | Not Started
2 | Cassette assembly - Qty 1 | 2026-04-29 | 2026-05-05 | 5 | Not Started |  | CNC Routed
2 | Use existing case ???? | 2026-04-29 | 2026-04-29 | 1 | Not Started |  | CNC Routed
1 | Lab Testing | 2026-05-06 | 2026-06-02 | 20 | Not Started
2 | Initial design Comparison | 2026-05-06 | 2026-06-02 | 20 | Not Started |  | Building prototypes
2 | NSF | 2026-05-13 | 2026-05-19 | 5 | Not Started
2 | DOE | 2026-05-20 | 2026-05-26 | 5 | Not Started
1 | Buy parts - Production prototypes | 2026-05-13 | 2026-07-22 | 51 | Not Started |  | Initial design Comparison
2 | Enclosure | 2026-05-13 | 2026-07-22 | 51 | Not Started |  | Initial design Comparison
3 | PO | 2026-05-13 | 2026-05-13 | 1 | Not Started |  | Initial design Comparison
3 | Sample delivery | 2026-05-14 | 2026-07-22 | 50 | Not Started
2 | Base | 2026-05-13 | 2026-07-22 | 51 | Not Started |  | Initial design Comparison
3 | PO | 2026-05-13 | 2026-05-13 | 1 | Not Started |  | Initial design Comparison
3 | Sample delivery | 2026-05-14 | 2026-07-22 | 50 | Not Started
2 | Electrical harness | 2026-05-13 | 2026-06-23 | 30 | Not Started |  | Initial design Comparison
1 | Lab testing - For production | 2026-07-23 | 2026-09-04 | 32 | Not Started
2 | UL | 2026-07-23 | 2026-09-04 | 32 | Not Started |  | Buy parts - Production prototypes
2 | DOE | 2026-07-23 | 2026-08-05 | 10 | Not Started |  | Buy parts - Production prototypes
2 | NSF | 2026-08-06 | 2026-08-19 | 10 | Not Started
1 | TC release | 2026-05-13 | 2026-06-04 | 17 | Not Started
2 | ENG Drawings | 2026-05-13 | 2026-05-26 | 10 | Not Started |  | Initial design Comparison
2 | TC BOMs | 2026-05-27 | 2026-06-02 | 5 | Not Started
2 | TC D1 complete | 2026-06-03 | 2026-06-04 | 2 | Not Started

## Project 1 Metadata
Field | Value
Owners | John, Sunil, Larry, Chris, Cody, Brett
Holidays | 2025-12-31, 2025-11-28, 2025-11-27, 2025-12-24, 2025-12-25, 2026-01-01
Exclude Weekends | Yes