## VAVE-MB 2.0 Tasks
Level | Task Name | Start | End | Duration | Status | Savings
2 | Cassette VAVE activities | 2026-06-05 | 2027-02-01 | 172 | In Progress | 165.5
3 | CAP Tube testing - MT | 2026-06-05 | 2026-09-04 | 66 | In Progress | 28 | have parts in house most likely. If not then it takes about 3 to 4 weeks. 6 weeks for implementation
4 | Hot box Validation - MT | 2026-06-05 | 2026-07-17 | 31 | In Progress
5 | Baseline run | 2026-06-05 | 2026-06-22 | 12 | Completed
5 | Captube trial 1 | 2026-06-23 | 2026-06-24 | 2 | Completed
5 | Captube trial 2 | 2026-06-25 | 2026-07-17 | 17 | In Progress
4 | Lab testing - 2Dr case | 2026-07-20 | 2026-07-24 | 5 | Not Started
4 | ECO Process | 2026-07-27 | 2026-08-07 | 10 | Not Started
4 | Tecumseh sourcing (Unknown) | 2026-08-10 | 2026-08-28 | 15 | Not Started
4 | Implementation | 2026-08-31 | 2026-09-04 | 5 | Not Started
3 | Check valve removal | 2026-07-20 | 2026-08-21 | 25 | Not Started | 5
4 | MS request - LT unit | 2026-07-30 | 2026-08-21 | 17 | Completed
4 | Hot box testing. | 2026-07-20 | 2026-07-24 | 5 | Not Started
3 | S/M - 1 (Removing parts/clamps from design) | 2026-06-08 | 2026-07-13 | 26 | In Progress | 7.5 | will get back on this timeline
4 | Transit test | 2026-06-08 | 2026-06-17 | 8 | Completed
4 | Vibration/sound test | 2026-06-18 | 2026-06-25 | 6 | Completed
4 | ECO process | 2026-06-26 | 2026-07-10 | 11 | In Progress
4 | Implementation | 2026-07-13 | 2026-07-13 | 1 | Not Started
3 | S/m - 2 (Control box redesign, evap shroud, compress base, cond. shroud) | 2026-06-05 | 2026-10-07 | 89 | In Progress | 30
4 | Design finalize | 2026-06-05 | 2026-06-23 | 13 | Completed
4 | MS request | 2026-06-24 | 2026-07-10 | 13 | In Progress
4 | MS work - complete | 2026-07-13 | 2026-07-24 | 10 | Not Started
4 | Ship to Tecumseh | 2026-07-27 | 2026-07-30 | 4 | Not Started
4 | Cassettes build | 2026-07-31 | 2026-08-13 | 10 | Not Started
4 | Ship to Hussmann | 2026-08-14 | 2026-08-20 | 5 | Not Started
4 | Transit test | 2026-08-21 | 2026-08-26 | 4 | Not Started
4 | Vibration test | 2026-08-27 | 2026-09-02 | 5 | Not Started
4 | ECO Process | 2026-09-03 | 2026-09-16 | 10 | Not Started
4 | Implementation timeline (Confirm inventory) | 2026-09-17 | 2026-10-07 | 15 | Not Started
3 | New enclosure for 2.0 (Molded foam/ Sm/ gasket) | 2026-06-05 | 2026-10-30 | 106 | In Progress | 20
4 | Concept design-1 (Roto mold) | 2026-06-05 | 2026-06-19 | 11 | Completed
4 | Concept design 2 (S/m cover design) | 2026-06-22 | 2026-07-10 | 15 | In Progress
4 | Quotes | 2026-07-13 | 2026-07-24 | 10 | Not Started
5 | sheetmetal - Victor Lopez | 2026-07-13 | 2026-07-17 | 5 | Not Started
5 | Molded foam Quotes - MTY/ATI | 2026-07-20 | 2026-07-24 | 5 | Not Started
4 | Prototypes - MS | 2026-07-13 | 2026-07-24 | 10 | Not Started
5 | 3D printed foam | 2026-07-13 | 2026-07-24 | 10 | Not Started
5 | S/m part | 2026-07-13 | 2026-07-17 | 5 | Not Started
5 | Gasket routing (Ray) | 2026-07-13 | 2026-07-24 | 10 | Not Started
4 | Initial Validation Test - on 2Dr case | 2026-07-27 | 2026-08-07 | 10 | Not Started
4 | Cut PO | 2026-08-10 | 2026-08-10 | 1 | Not Started
4 | Prototype samples | 2026-08-11 | 2026-10-09 | 44 | Not Started
4 | Lab testing | 2026-10-12 | 2026-10-30 | 15 | Not Started
5 | NSF | 2026-10-12 | 2026-10-16 | 5 | Not Started
5 | DOE | 2026-10-19 | 2026-10-30 | 10 | Not Started
4 | ECO Process | 2026-08-11 | 2026-08-28 | 14 | Not Started
4 | Implementation date | 2026-10-12 | 2026-10-23 | 10 | Not Started
3 | Aluminum coil | 2026-06-05 | 2027-02-01 | 172 | In Progress | 40
4 | MT Aluminum coil | 2026-06-05 | 2027-02-01 | 172 | In Progress
5 | Define coil spec. Drawings? | 2026-06-05 | 2026-06-18 | 10 | Completed
5 | Request for quotes. Send dwgs | 2026-06-19 | 2026-06-23 | 3 | Completed
5 | Get quotes/Timelines from supplier | 2026-06-24 | 2026-07-17 | 18 | In Progress
5 | Request samples- Send PO | 2026-07-20 | 2026-07-24 | 5 | Not Started
5 | Receive samples | 2026-07-27 | 2026-10-12 | 56 | Not Started
5 | Lab testing | 2026-10-13 | 2026-10-26 | 10 | Not Started
6 | NSF | 2026-10-13 | 2026-10-19 | 5 | Not Started
6 | DOE | 2026-10-20 | 2026-10-26 | 5 | Not Started
5 | ECO process | 2026-10-20 | 2026-11-02 | 10 | Not Started
5 | Order parts | 2026-11-03 | 2027-01-11 | 50 | Not Started
5 | Implementation date | 2027-01-12 | 2027-02-01 | 15 | Not Started
4 | LT Aluminum coil | 2026-06-05 | 2027-02-01 | 172 | In Progress
5 | Define coil spec. Drawings? | 2026-06-05 | 2026-06-18 | 10 | Completed
5 | Request for quotes. Send dwgs | 2026-06-19 | 2026-06-23 | 3 | Completed
5 | Get quotes/Timelines from supplier | 2026-06-24 | 2026-07-17 | 18 | In Progress
5 | Request samples- Send PO | 2026-07-20 | 2026-07-24 | 5 | Not Started
5 | Receive samples | 2026-07-27 | 2026-10-12 | 56 | Not Started
5 | Lab testing | 2026-10-13 | 2026-10-26 | 10 | Not Started
6 | NSF | 2026-10-13 | 2026-10-19 | 5 | Not Started
6 | DOE | 2026-10-20 | 2026-10-26 | 5 | Not Started
5 | ECO process | 2026-10-20 | 2026-11-02 | 10 | Not Started
5 | Order parts | 2026-11-03 | 2027-01-11 | 50 | Not Started
5 | Implementation date | 2027-01-12 | 2027-02-01 | 15 | Not Started
3 | Cheaper Carel controller | 2026-06-05 | 2026-09-16 | 74 | In Progress | 15
4 | Carel discussion - new part number initiation | 2026-06-05 | 2026-06-22 | 12 | Completed
4 | New wiring diagrams | 2026-06-23 | 2026-07-13 | 15 | In Progress
4 | Quote | 2026-07-14 | 2026-07-20 | 5 | Not Started
4 | Initiate Sample PO | 2026-07-21 | 2026-07-27 | 5 | Not Started
4 | Samples | 2026-07-28 | 2026-08-10 | 10 | Not Started
4 | Bench testing | 2026-08-11 | 2026-08-17 | 5 | Not Started
4 | Initiate production PO | 2026-08-18 | 2026-08-18 | 1 | Not Started
4 | ECO process | 2026-08-19 | 2026-09-01 | 10 | Not Started
4 | Procure parts for production | 2026-08-19 | 2026-09-15 | 20 | Not Started
4 | Implementation date | 2026-09-16 | 2026-09-16 | 1 | Not Started
3 | Tube on drip tray | 2026-07-08 | 2026-07-24 | 13 | In Progress | 0
4 | Design validation | 2026-07-08 | 2026-07-09 | 2 | In Progress
4 | ECO process | 2026-07-10 | 2026-07-23 | 10 | Not Started
4 | Procure parts | 2026-07-10 | 2026-07-23 | 10 | Not Started
4 | Implementation | 2026-07-24 | 2026-07-24 | 1 | Not Started
3 | Harness design | 2026-06-05 | 2026-09-17 | 75 | In Progress | 20
4 | Drawing to supplier | 2026-06-05 | 2026-06-26 | 16 | Completed
4 | Quote | 2026-06-29 | 2026-07-15 | 13 | In Progress
4 | PO for samples | 2026-07-16 | 2026-07-16 | 1 | Not Started
4 | Samples | 2026-07-17 | 2026-08-20 | 25 | Not Started
4 | Validation | 2026-08-21 | 2026-08-27 | 5 | Not Started
4 | Eco Process | 2026-08-28 | 2026-09-10 | 10 | Not Started
4 | Implementation date | 2026-09-11 | 2026-09-17 | 5 | Not Started
2 | Case VAVE activities | 2026-06-26 | 2026-09-18 | 61 | In Progress | 78.29
3 | Plastic Deck Pans | 2026-06-26 | 2026-09-18 | 61 | In Progress | 26.65
4 | LAb request | 2026-06-26 | 2026-07-31 | 26 | In Progress
4 | Lab test base line | 2026-08-03 | 2026-08-14 | 10 | Not Started
4 | Lab test new deck pans | 2026-08-17 | 2026-08-21 | 5 | Not Started
4 | ECN release process | 2026-08-24 | 2026-09-11 | 15 | Not Started
4 | Implementation date | 2026-09-14 | 2026-09-18 | 5 | Not Started
3 | Simplify Raceway | 2026-06-26 | 2026-08-07 | 31 | In Progress | 3.07
4 | Design changes | 2026-06-26 | 2026-07-10 | 11 | In Progress
4 | ECN Release | 2026-07-13 | 2026-08-07 | 20 | Not Started
3 | Case power cord | 2026-06-26 | 2026-09-01 | 48 | In Progress | 5.49
4 | Design changes | 2026-06-26 | 2026-07-14 | 13 | In Progress
4 | Seperate ECN ( sourcing task) | 2026-07-15 | 2026-09-01 | 35 | Not Started
3 | 10Amp Breaker | 2026-06-26 | 2026-08-11 | 33 | In Progress | 32.56
4 | Design changes | 2026-06-26 | 2026-07-14 | 13 | In Progress
4 | ECN Release | 2026-07-15 | 2026-08-11 | 20 | Not Started
3 | Simplify Under Door Support | 2026-06-26 | 2026-08-07 | 31 | In Progress | 1.48
4 | Design changes | 2026-06-26 | 2026-07-10 | 11 | In Progress
4 | ECN Release | 2026-07-13 | 2026-08-07 | 20 | Not Started
3 | Reduce Qty of Canopy Foam Backers | 2026-06-26 | 2026-08-07 | 31 | In Progress | 5.27
4 | Design changes | 2026-06-26 | 2026-07-10 | 11 | In Progress
4 | ECN Release | 2026-07-13 | 2026-08-07 | 20 | Not Started
3 | Remove Drain | 2026-06-26 | 2026-08-12 | 34 | In Progress | 3.77
4 | Design changes | 2026-06-26 | 2026-07-15 | 14 | In Progress
4 | ECN Release | 2026-07-16 | 2026-08-12 | 20 | Not Started
3 | Tariff | 2026-06-26 | Completed |  |  | 43.26

## Summary
| RMN5MA | RMN4MA | RMN3MA | RMN2MA | RLN5MA | RLN4MA | RLN3MA | RLN2MA
# of cassettes | 2 | 2 | 2 | 1 | 3 | 2 | 2 | 1
VAVE Savings - Cassettes | 410.82 | 410.82 | 410.82 | 205.41 | 631.23 | 420.82 | 420.82 | 210.41
VAVE Savings - Case | 81.9827 | 78.5868 | 75.1909 | 64.7683 | 81.9827 | 78.5868 | 75.1909 | 64.7683
Total VAVE savings | 492.8027 | 489.4068 | 486.0109 | 270.1783 | 713.2127 | 499.4068 | 496.0109 | 275.1783
Savings realized - Cassette | 86.52 | 86.52 | 86.52 | 43.26 | 129.78 | 86.52 | 86.52 | 43.26
Savings realized - Case | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total savings realized | 86.52 | 86.52 | 86.52 | 43.26 | 129.78 | 86.52 | 86.52 | 43.26