## DG- 5Dr LT Tasks
Level | Task Name | Start | End | Duration | Status | Owner | Depends On | Notes
0 | DG-5DR-LT | 2026-04-22 | 2026-07-29 | 71 | In Progress
1 | Engineering work -1 | 2026-04-22 | 2026-06-30 | 50 | In Progress
2 | Prototype drawings - for MS | 2026-04-22 | 2026-04-28 | 5 | In Progress
2 | Target kit work | 2026-04-22 | 2026-05-26 | 25 | In Progress
3 | Slim handle | 2026-04-22 | 2026-05-11 | 14 | In Progress
3 | Splashguard with fan | 2026-04-22 | 2026-05-11 | 14 | In Progress
3 | LH/RH foam LT end panels w/optional color trim | 2026-04-22 | 2026-05-11 | 14 | In Progress
3 | LH/RH foam MT end panels w/optional color trim | 2026-04-22 | 2026-05-11 | 14 | In Progress
3 | 2in insulated partition (LH/RH) | 2026-04-22 | 2026-05-11 | 14 | In Progress
3 | Plexi partition | 2026-04-22 | 2026-05-11 | 14 | In Progress
3 | No control display - Rotate control box | 2026-04-22 | 2026-05-11 | 14 | In Progress
3 | Joining kit | 2026-04-22 | 2026-05-11 | 14 | In Progress
3 | wire racks ( 1in lip) | 2026-04-22 | 2026-05-11 | 14 | In Progress
3 | Wire racks ( 2"/4" lip) | 2026-04-22 | 2026-05-11 | 14 | In Progress
3 | Dual end bumper | 2026-04-22 | 2026-05-11 | 14 | In Progress
3 | Case structure kit w/o ends | 2026-04-22 | 2026-05-26 | 25 | In Progress
2 | Order parts | 2026-04-22 | 2026-06-30 | 50 | In Progress
3 | Cases delivery | 2026-04-22 | 2026-06-30 | 50 | In Progress
3 | Case canopy delivery | 2026-04-22 | 2026-05-19 | 20 | In Progress
3 | Cassettes delivery | 2026-04-22 | 2026-05-13 | 16 | In Progress
3 | Electrical plug and other parts | 2026-04-22 | 2026-04-23 | 2 | In Progress
2 | TC work | 2026-04-29 | 2026-06-02 | 25 | Not Started
3 | 5Dr TC release | 2026-04-29 | 2026-05-05 | 5 | Not Started |  | Prototype drawings - for MS
3 | Target kit release | 2026-05-27 | 2026-06-02 | 5 | Not Started |  | Target kit work
2 | HPC | 2026-06-03 | 2026-06-09 | 5 | Not Started |  | Target kit release
1 | Model shop work | 2026-05-20 | 2026-07-07 | 35 | Not Started
2 | Convert MT canopy to LT | 2026-05-20 | 2026-05-26 | 5 | Not Started |  | Case canopy delivery
2 | Modify DG case with new structure | 2026-07-01 | 2026-07-07 | 5 | Not Started |  | Cases delivery
1 | Testing | 2026-04-22 | 2026-07-29 | 71 | In Progress
2 | Simulation | 2026-04-22 | 2026-05-15 | 18 | In Progress
3 | CFD | 2026-04-22 | 2026-05-15 | 18 | In Progress
3 | FEA | 2026-04-22 | 2026-05-08 | 13 | In Progress
2 | TESTING | 2026-04-22 | 2026-07-29 | 71 | In Progress
3 | Structural testing | 2026-07-08 | 2026-07-29 | 16 | Not Started
4 | Case load test - 1 | 2026-07-08 | 2026-07-10 | 3 | Not Started |  | Modify DG case with new structure
4 | Case load test - 2 | 2026-07-13 | 2026-07-24 | 10 | Not Started
4 | Transit test | 2026-07-27 | 2026-07-29 | 3 | Not Started
3 | Performance Testing | 2026-04-22 | 2026-07-14 | 60 | In Progress
4 | 5Dr LT | 2026-05-27 | 2026-07-07 | 30 | Not Started |  | Modify DG case with new structure
5 | DOE | 2026-05-27 | 2026-06-02 | 5 | Not Started |  | Convert MT canopy to LT
5 | NSF | 2026-06-03 | 2026-06-09 | 5 | Not Started
5 | Target spec perf test | 2026-06-10 | 2026-06-16 | 5 | Not Started
5 | UL | 2026-06-17 | 2026-07-07 | 15 | Not Started
4 | 4Dr - 3Dr with acrylic partition | 2026-07-01 | 2026-07-14 | 10 | Not Started |  | Cases delivery | [2026-04-22]: Longest pole in the tent
4 | 3Dr LT - Target spec | 2026-04-22 | 2026-04-28 | 5 | In Progress
4 | Target dual temp - 3Dr | 2026-04-22 | 2026-05-11 | 14 | In Progress
1 | Engineering work - 2 (Changes after testing) | 2026-06-10 | 2026-06-30 | 15 | Not Started
2 | Production drawings - Round 2. Testing changes | 2026-06-10 | 2026-06-16 | 5 | Not Started |  | NSF
2 | TC Round 2 release - If changes come from testing | 2026-06-17 | 2026-06-30 | 10 | Not Started |  | Production drawings - Round 2. Testing changes
1 | Placing orders in HPC | 2026-07-01 | 2026-07-01 | 1 | Not Started |  | TC Round 2 release - If changes come from testing

## DG- 5Dr LT Metadata
Field | Value
Owners | Unassigned, Me
Holidays
Exclude Weekends | Yes