## VAVE-MB 2.0 Tasks
Level | Task Name | Start | End | Duration | Status | Owner | Depends On | Notes
0 | DG- VAVE short term | 2026-06-05 | 2027-02-01 | 172 | In Progress
1 | Prep - Order parts | 2026-06-05 | 2026-07-29 | 39 | Completed
2 | VAVE brain storm session | 2026-06-05 | 2026-06-25 | 15 | Completed
2 | Parts list to sourcing for quotes | 2026-06-26 | 2026-07-01 | 4 | Completed
2 | Order parts - Lab testing | 2026-07-02 | 2026-07-29 | 20 | Completed
3 | Cassettes | 2026-07-02 | 2026-07-15 | 10 | Completed
3 | Cases | 2026-07-16 | 2026-07-29 | 10 | Completed
1 | VAVE activities | 2026-06-05 | 2027-02-01 | 172 | In Progress
2 | Cassette VAVE activities | 2026-06-05 | 2027-02-01 | 172 | In Progress
3 | CAP Tube testing - MT | 2026-06-05 | 2026-09-04 | 66 | In Progress
4 | Hot box Validation - MT | 2026-06-05 | 2026-07-17 | 31 | In Progress |  |  | [2026-07-07]: Cut 18" off of the captube. no change on SH [2026-06-23]: Initial baseline run done. Should get a captube result by tomorrow
5 | Baseline run | 2026-06-05 | 2026-06-22 | 12 | Completed
5 | Captube trial 1 | 2026-06-23 | 2026-06-24 | 2 | Completed |  |  | [2026-06-25]: High superheat. Cut the captube down by 10in
5 | Captube trial 2 | 2026-06-25 | 2026-07-17 | 17 | In Progress |  |  | [2026-07-09]: Delayed +13d, end -> 2026-07-17. Nothing seems to be changing on cassette. already cut 18in off. Initial analysis might have been done with wrong inputs. Chris doing the analysis again and we will probably use 0.049" captube
4 | Lab testing - 2Dr case | 2026-07-20 | 2026-07-24 | 5 | Not Started |  |  | [2026-07-09]: Delayed +4d, end -> 2026-07-24.
4 | ECO Process | 2026-07-27 | 2026-08-07 | 10 | Not Started |  |  | [2026-07-09]: Delayed +9d, end -> 2026-08-07.
4 | Tecumseh sourcing (Unknown) | 2026-08-10 | 2026-08-28 | 15 | Not Started |  |  | [2026-07-09]: Delayed +14d, end -> 2026-08-28.
4 | Implementation | 2026-08-31 | 2026-09-04 | 5 | Not Started |  |  | [2026-07-09]: Delayed +4d, end -> 2026-09-04.
3 | Check valve removal | 2026-07-20 | 2026-08-21 | 25 | Not Started
4 | MS request - LT unit | 2026-07-30 | 2026-08-21 | 17 | Completed
4 | Hot box testing. | 2026-07-20 | 2026-07-24 | 5 | Not Started |  | Captube trial 2
3 | S/M - 1 (Removing parts/clamps from design) | 2026-06-08 | 2026-08-03 | 41 | In Progress
4 | Transit test | 2026-06-08 | 2026-06-17 | 8 | Completed |  |  | [2026-06-16]: Tecumseh just sent additional sm parts. Would like to test it all at once on the transit test. [2026-06-15]: Chris already put in a lab test request
4 | Vibration/sound test | 2026-06-18 | 2026-06-25 | 6 | Completed |  |  | [2026-06-15]: Chris put in the request
4 | ECO process | 2026-06-26 | 2026-07-10 | 11 | In Progress
4 | Older parts phase out | 2026-07-13 | 2026-07-31 | 15 | Not Started |  |  | [2026-07-09]: Delayed +14d, end -> 2026-07-31.
4 | Implementation | 2026-08-03 | 2026-08-03 | 1 | Not Started
3 | S/m - 2 (Control box redesign, evap shroud, compress base, cond. shroud) | 2026-06-05 | 2026-10-07 | 89 | In Progress
4 | Design finalize | 2026-06-05 | 2026-06-23 | 13 | Completed
4 | MS request | 2026-06-24 | 2026-07-10 | 13 | In Progress
4 | MS work - complete | 2026-07-13 | 2026-07-24 | 10 | Not Started |  |  | [2026-07-09]: Delayed +9d, end -> 2026-07-24.
4 | Ship to Tecumseh | 2026-07-27 | 2026-07-30 | 4 | Not Started
4 | Cassettes build | 2026-07-31 | 2026-08-13 | 10 | Not Started |  |  | [2026-07-09]: Delayed +5d, end -> 2026-07-30. [2026-07-09]: Delayed +4d, end -> 2026-07-21.
4 | Ship to Hussmann | 2026-08-14 | 2026-08-20 | 5 | Not Started |  |  | [2026-07-09]: Delayed +4d, end -> 2026-08-06.
4 | Transit test | 2026-08-21 | 2026-08-26 | 4 | Not Started |  |  | [2026-07-09]: Delayed +3d, end -> 2026-08-12.
4 | Vibration test | 2026-08-27 | 2026-09-02 | 5 | Not Started
4 | ECO Process | 2026-09-03 | 2026-09-16 | 10 | Not Started
4 | Implementation timeline (Confirm inventory) | 2026-09-17 | 2026-10-07 | 15 | Not Started |  |  | [2026-07-09]: Delayed +14d, end -> 2026-09-23.
3 | New enclosure for 2.0 (Molded foam/ Sm/ gasket) | 2026-06-05 | 2026-10-30 | 106 | In Progress
4 | Concept design-1 (Roto mold) | 2026-06-05 | 2026-06-19 | 11 | Completed |  |  | [2026-07-09]: Does not work. Costs more than $75 [2026-06-23]: Sent out quotes for roto molding. Waiting to hear back
4 | Concept design 2 (S/m cover design) | 2026-06-22 | 2026-07-10 | 15 | In Progress
4 | Quotes | 2026-07-13 | 2026-07-24 | 10 | Not Started |  |  | [2026-06-30]: Quotes dont look that good. Looking into other options.
5 | sheetmetal - Victor Lopez | 2026-07-13 | 2026-07-17 | 5 | Not Started |  |  | [2026-07-09]: Delayed +4d, end -> 2026-07-17.
5 | Molded foam Quotes - MTY/ATI | 2026-07-20 | 2026-07-24 | 5 | Not Started |  |  | [2026-07-09]: Delayed +4d, end -> 2026-07-24.
4 | Prototypes - MS | 2026-07-13 | 2026-07-24 | 10 | Not Started |  | Concept design 2 (S/m cover design)
5 | 3D printed foam | 2026-07-13 | 2026-07-24 | 10 | Not Started |  |  | [2026-07-09]: Delayed +9d, end -> 2026-07-24.
5 | S/m part | 2026-07-13 | 2026-07-17 | 5 | Not Started |  | Concept design 2 (S/m cover design) | [2026-07-09]: Delayed +4d, end -> 2026-07-31.
5 | Gasket routing (Ray) | 2026-07-13 | 2026-07-24 | 10 | Not Started |  | Concept design 2 (S/m cover design) | [2026-07-09]: Delayed +9d, end -> 2026-07-24.
4 | Initial Validation Test - on 2Dr case | 2026-07-27 | 2026-08-07 | 10 | Not Started
4 | Cut PO | 2026-08-10 | 2026-08-10 | 1 | Not Started
4 | Prototype samples | 2026-08-11 | 2026-10-09 | 44 | Not Started |  |  | [2026-07-09]: Delayed +9d, end -> 2026-10-09.
4 | Lab testing | 2026-10-12 | 2026-10-30 | 15 | Not Started
5 | NSF | 2026-10-12 | 2026-10-16 | 5 | Not Started
5 | DOE | 2026-10-19 | 2026-10-30 | 10 | Not Started
4 | ECO Process | 2026-08-11 | 2026-08-28 | 14 | Not Started |  | Cut PO | [2026-07-09]: Delayed +13d, end -> 2026-08-27.
4 | Implementation date | 2026-10-12 | 2026-10-23 | 10 | Not Started |  | Prototype samples | [2026-07-09]: Delayed +9d, end -> 2026-10-23.
3 | Aluminum coil | 2026-06-05 | 2027-02-01 | 172 | In Progress
4 | MT Aluminum coil | 2026-06-05 | 2027-02-01 | 172 | In Progress
5 | Define coil spec. Drawings? | 2026-06-05 | 2026-06-18 | 10 | Completed |  |  | [2026-06-16]: Got the first result. Aluminum coil used for locker has the same or better performance. Asked Wendy to evaluate current coil with Al material
5 | Request for quotes. Send dwgs | 2026-06-19 | 2026-06-23 | 3 | Completed
5 | Get quotes/Timelines from supplier | 2026-06-24 | 2026-07-17 | 18 | In Progress
5 | Request samples- Send PO | 2026-07-20 | 2026-07-24 | 5 | Not Started
5 | Receive samples | 2026-07-27 | 2026-10-12 | 56 | Not Started
5 | Lab testing | 2026-10-13 | 2026-10-26 | 10 | Not Started
6 | NSF | 2026-10-13 | 2026-10-19 | 5 | Not Started
6 | DOE | 2026-10-20 | 2026-10-26 | 5 | Not Started
5 | ECO process | 2026-10-20 | 2026-11-02 | 10 | Not Started |  | NSF | [2026-07-09]: Delayed +9d, end -> 2026-11-02.
5 | Order parts | 2026-11-03 | 2027-01-11 | 50 | Not Started |  |  | [2026-07-09]: Delayed +49d, end -> 2027-01-11.
5 | Implementation date | 2027-01-12 | 2027-02-01 | 15 | Not Started |  |  | [2026-07-09]: Delayed +14d, end -> 2027-02-01.
4 | LT Aluminum coil | 2026-06-05 | 2027-02-01 | 172 | In Progress
5 | Define coil spec. Drawings? | 2026-06-05 | 2026-06-18 | 10 | Completed |  |  | [2026-06-16]: Got the first result. Aluminum coil used for locker has the same or better performance. Asked Wendy to evaluate current coil with Al material
5 | Request for quotes. Send dwgs | 2026-06-19 | 2026-06-23 | 3 | Completed
5 | Get quotes/Timelines from supplier | 2026-06-24 | 2026-07-17 | 18 | In Progress
5 | Request samples- Send PO | 2026-07-20 | 2026-07-24 | 5 | Not Started
5 | Receive samples | 2026-07-27 | 2026-10-12 | 56 | Not Started
5 | Lab testing | 2026-10-13 | 2026-10-26 | 10 | Not Started
6 | NSF | 2026-10-13 | 2026-10-19 | 5 | Not Started
6 | DOE | 2026-10-20 | 2026-10-26 | 5 | Not Started
5 | ECO process | 2026-10-20 | 2026-11-02 | 10 | Not Started |  | NSF | [2026-07-09]: Delayed +9d, end -> 2026-11-02.
5 | Order parts | 2026-11-03 | 2027-01-11 | 50 | Not Started |  |  | [2026-07-09]: Delayed +49d, end -> 2027-01-11.
5 | Implementation date | 2027-01-12 | 2027-02-01 | 15 | Not Started |  |  | [2026-07-09]: Delayed +14d, end -> 2027-02-01.
3 | Cheaper Carel controller | 2026-06-05 | 2026-09-16 | 74 | In Progress
4 | Carel discussion - new part number initiation | 2026-06-05 | 2026-06-22 | 12 | Completed
4 | New wiring diagrams | 2026-06-23 | 2026-07-13 | 15 | In Progress |  |  | [2026-07-09]: Delayed +5d, end -> 2026-07-13.
4 | Quote | 2026-07-14 | 2026-07-20 | 5 | Not Started
4 | Initiate Sample PO | 2026-07-21 | 2026-07-27 | 5 | Not Started
4 | Samples | 2026-07-28 | 2026-08-10 | 10 | Not Started
4 | Bench testing | 2026-08-11 | 2026-08-17 | 5 | Not Started
4 | Initiate production PO | 2026-08-18 | 2026-08-18 | 1 | Not Started
4 | ECO process | 2026-08-19 | 2026-09-01 | 10 | Not Started
4 | Procure parts for production | 2026-08-19 | 2026-09-15 | 20 | Not Started |  | Initiate production PO | [2026-07-09]: Delayed +19d, end -> 2026-09-08.
4 | Implementation date | 2026-09-16 | 2026-09-16 | 1 | Not Started
3 | Tube on drip tray | 2026-07-08 | 2026-07-24 | 13 | In Progress
4 | Design validation | 2026-07-08 | 2026-07-09 | 2 | In Progress |  |  | [2026-07-09]: Delayed +1d, end -> 2026-07-10.
4 | ECO process | 2026-07-10 | 2026-07-23 | 10 | Not Started |  |  | [2026-07-09]: Delayed +9d, end -> 2026-07-24.
4 | Procure parts | 2026-07-10 | 2026-07-23 | 10 | Not Started |  | Design validation | [2026-07-09]: Delayed +9d, end -> 2026-08-07.
4 | Implementation | 2026-07-24 | 2026-07-24 | 1 | Not Started
3 | Harness design | 2026-06-05 | 2026-09-17 | 75 | In Progress
4 | Drawing to supplier | 2026-06-05 | 2026-06-26 | 16 | Completed |  |  | [2026-07-09]: Delayed +15d, end -> 2026-06-26.
4 | Quote | 2026-06-29 | 2026-07-15 | 13 | In Progress |  |  | [2026-07-09]: Delayed +12d, end -> 2026-07-15.
4 | PO for samples | 2026-07-16 | 2026-07-16 | 1 | Not Started
4 | Samples | 2026-07-17 | 2026-08-20 | 25 | Not Started |  |  | [2026-07-09]: Delayed +5d, end -> 2026-08-20. [2026-07-09]: Delayed +19d, end -> 2026-08-13.
4 | Validation | 2026-08-21 | 2026-08-27 | 5 | Not Started |  |  | [2026-07-09]: Delayed +4d, end -> 2026-08-20.
4 | Eco Process | 2026-08-28 | 2026-09-10 | 10 | Not Started |  |  | [2026-07-09]: Delayed +9d, end -> 2026-09-03.
4 | Implementation date | 2026-09-11 | 2026-09-17 | 5 | Not Started |  |  | [2026-07-09]: Delayed +4d, end -> 2026-09-10.
3 | Evap/ Condenser fan - 3 qty | 2026-06-26 | 2026-08-28 | 46 | In Progress
4 | Initial fan curve evaluation | 2026-06-26 | 2026-07-02 | 5 | Completed |  |  | [2026-07-09]: Delayed +4d, end -> 2026-07-02.
4 | Sample order - | 2026-07-03 | 2026-07-23 | 15 | In Progress |  |  | [2026-07-09]: Delayed +14d, end -> 2026-07-23.
4 | Wind tunnel testing | 2026-07-24 | 2026-07-30 | 5 | Not Started |  |  | [2026-07-09]: Delayed +4d, end -> 2026-07-30.
4 | Performance testing - NSF | 2026-07-31 | 2026-08-13 | 10 | Not Started |  |  | [2026-07-09]: Delayed +9d, end -> 2026-08-13.
4 | DOE | 2026-08-14 | 2026-08-27 | 10 | Not Started |  |  | [2026-07-09]: Delayed +9d, end -> 2026-08-27.
4 | ECO process | 2026-08-14 | 2026-08-27 | 10 | Not Started |  | Performance testing - NSF | [2026-07-09]: Delayed +9d, end -> 2026-09-10.
4 | Implementation date | 2026-08-28 | 2026-08-28 | 1 | Not Started
3 | Pallet - CArdboard design | 2026-06-05 | 2026-09-28 | 82 | In Progress
4 | Design update | 2026-06-05 | 2026-06-12 | 6 | Completed |  |  | [2026-07-09]: Delayed +5d, end -> 2026-06-12.
4 | Quote | 2026-06-15 | 2026-07-17 | 25 | In Progress |  |  | [2026-07-09]: Delayed +24d, end -> 2026-07-17.
4 | Samples to Tecum | 2026-07-20 | 2026-08-07 | 15 | Not Started |  |  | [2026-07-09]: Delayed +14d, end -> 2026-08-07.
4 | Ship 3 samples to BGN | 2026-08-10 | 2026-08-21 | 10 | Not Started |  |  | [2026-07-09]: Delayed +9d, end -> 2026-08-21.
4 | Transit test - triple stack | 2026-08-24 | 2026-09-04 | 10 | Not Started |  |  | [2026-07-09]: Delayed +9d, end -> 2026-09-04.
4 | Pressure test | 2026-09-07 | 2026-09-11 | 5 | Not Started |  |  | [2026-07-09]: Delayed +4d, end -> 2026-09-11.
4 | ECO Process | 2026-09-14 | 2026-09-25 | 10 | Not Started |  |  | [2026-07-09]: Delayed +9d, end -> 2026-09-25.
4 | Implementation date | 2026-09-28 | 2026-09-28 | 1 | Not Started
3 | Tariff - MT | 2026-06-05 | 2026-06-15 | 7 | Completed
4 | Implementation date | 2026-06-05 | 2026-06-15 | 7 | Completed |  |  | [2026-07-09]: Delayed +6d, end -> 2026-06-15.
3 | Tariff - LT | 2026-06-05 | 2026-06-15 | 7 | Completed
4 | Implementation date | 2026-06-05 | 2026-06-15 | 7 | Completed |  |  | [2026-07-09]: Delayed +6d, end -> 2026-06-15.
2 | Case VAVE activities | 2026-06-26 | 2026-09-18 | 61 | In Progress
3 | Plastic Deck Pans | 2026-06-26 | 2026-09-18 | 61 | In Progress
4 | LAb request | 2026-06-26 | 2026-07-31 | 26 | In Progress |  |  | [2026-07-09]: Delayed +25d, end -> 2026-07-10.
4 | Lab test base line | 2026-08-03 | 2026-08-14 | 10 | Not Started |  |  | [2026-07-09]: Delayed +9d, end -> 2026-07-24.
4 | Lab test new deck pans | 2026-08-17 | 2026-08-21 | 5 | Not Started |  |  | [2026-07-09]: Delayed +4d, end -> 2026-07-31.
4 | ECN release process | 2026-08-24 | 2026-09-11 | 15 | Not Started |  |  | [2026-07-09]: Delayed +14d, end -> 2026-08-21.
4 | Implementation date | 2026-09-14 | 2026-09-18 | 5 | Not Started |  |  | [2026-07-09]: Delayed +4d, end -> 2026-08-28.
3 | Simplify Raceway | 2026-06-26 | 2026-08-07 | 31 | In Progress
4 | Design changes | 2026-06-26 | 2026-07-10 | 11 | In Progress |  |  | [2026-07-09]: Delayed +10d, end -> 2026-07-10.
4 | ECN Release | 2026-07-13 | 2026-08-07 | 20 | Not Started |  |  | [2026-07-09]: Delayed +19d, end -> 2026-08-07.
3 | Case power cord | 2026-06-26 | 2026-09-01 | 48 | In Progress
4 | Design changes | 2026-06-26 | 2026-07-14 | 13 | In Progress |  |  | [2026-07-09]: Delayed +2d, end -> 2026-07-14. [2026-07-09]: Delayed +10d, end -> 2026-07-10.
4 | Seperate ECN ( sourcing task) | 2026-07-15 | 2026-09-01 | 35 | Not Started |  |  | [2026-07-09]: Delayed +34d, end -> 2026-09-01.
3 | 10Amp Breaker | 2026-06-26 | 2026-08-11 | 33 | In Progress
4 | Design changes | 2026-06-26 | 2026-07-14 | 13 | In Progress |  |  | [2026-07-09]: Delayed +2d, end -> 2026-07-14. [2026-07-09]: Delayed +10d, end -> 2026-07-10.
4 | ECN Release | 2026-07-15 | 2026-08-11 | 20 | Not Started |  |  | [2026-07-09]: Delayed +19d, end -> 2026-08-11.
3 | Simplify Under Door Support | 2026-06-26 | 2026-08-07 | 31 | In Progress
4 | Design changes | 2026-06-26 | 2026-07-10 | 11 | In Progress |  |  | [2026-07-09]: Delayed +10d, end -> 2026-07-10.
4 | ECN Release | 2026-07-13 | 2026-08-07 | 20 | Not Started |  |  | [2026-07-09]: Delayed +19d, end -> 2026-08-07.
3 | Reduce Qty of Canopy Foam Backers | 2026-06-26 | 2026-08-07 | 31 | In Progress
4 | Design changes | 2026-06-26 | 2026-07-10 | 11 | In Progress |  |  | [2026-07-09]: Delayed +10d, end -> 2026-07-10.
4 | ECN Release | 2026-07-13 | 2026-08-07 | 20 | Not Started |  |  | [2026-07-09]: Delayed +19d, end -> 2026-08-07.
3 | Remove Drain | 2026-06-26 | 2026-08-12 | 34 | In Progress
4 | Design changes | 2026-06-26 | 2026-07-15 | 14 | In Progress |  |  | [2026-07-09]: Delayed +13d, end -> 2026-07-15.
4 | ECN Release | 2026-07-16 | 2026-08-12 | 20 | Not Started |  |  | [2026-07-09]: Delayed +19d, end -> 2026-08-12.

## VAVE-MB 2.0 Metadata
Field | Value
Owners | Unassigned, Me
Holidays
Exclude Weekends | Yes